## Dashboard
AWS Infrastructure Upgrade Tracker - Dashboard
Last Updated: 2026-02-04 08:33
SUMMARY STATISTICS
Status | Count |  | Environment | Count |  | Risk Level | Count | Component | Count
Not Started | 2 |  | QA | 4 |  | Critical | 1 | EKS | 1
In Progress | 2 |  | UAT | 2 |  | High | 3 | RDS | 1
Blocked | 1 |  | PROD | 2 |  | Medium | 2 | ALB | 1
Ready for Deploy | 1 |  |  |  |  | Low | 2 | ElastiCache | 1
Deployed | 1 | [6 empty] | API Gateway | 1
Validated | 1 | [6 empty] | Aurora | 1
Rolled Back | 0 | [6 empty] | Lambda | 1
[8 empty] | CloudFront | 1
UPCOMING MAINTENANCE WINDOWS
Date | Component | Environment | Window | Owner | Status
2026-02-15 | EKS Cluster | QA | 02:00-06:00 | John Smith | In Progress
2026-02-18 | ALB | UAT | 00:00-02:00 | Mike Chen | Ready for Deploy
2026-02-20 | RDS PostgreSQL | QA | 03:00-07:00 | Sarah Johnson | Not Started
2026-02-22 | ElastiCache | QA | 04:00-06:00 | Emily Davis | In Progress
2026-02-25 | Aurora MySQL | UAT | 01:00-05:00 | Sarah Johnson | Blocked
ALERTS & ACTION ITEMS
1 upgrade is BLOCKED - Aurora MySQL 8.0 (UPG-006) - Query compatibility issues
1 Critical risk item pending - API Gateway v2 Migration (UPG-005)
3 upgrades with High risk level require additional review
2 upgrades scheduled in next 7 days

## Upgrade Backlog
ID | Title | Service/Component | Current Version | Target Version | Environment | Region/VPC | Owner | Team | Priority | Risk Level | Customer Impact | Downtime Expected | Maintenance Window | Dependencies | Rollback Plan | Runbook | Status | Start Date | Target Date | Completed Date | Validation Checklist | Evidence | Notes
UPG-001 | EKS Cluster Upgrade to 1.29 | EKS | 1.27 | 1.29 | QA | us-east-1 | John Smith | Platform | P1 - Critical | High | Medium | Yes | 2026-02-15 02:00-06:00 | Node group upgrade | [Link] | [Link] | In Progress | 2026-02-01 | 2026-02-15 |  | [Link] | [Link]
UPG-002 | RDS PostgreSQL Upgrade to 16 | RDS | 14.9 | 16.1 | QA | us-east-1 | Sarah Johnson | Database | P2 - High | High | High | Yes | 2026-02-20 03:00-07:00 | Application compatibility testing | [Link] | [Link] | Not Started | 2026-02-10 | 2026-02-20 |  | [Link] | [Link]
UPG-003 | ALB to latest firmware | ALB | Current | Latest | UAT | us-east-1 | Mike Chen | Network | P3 - Medium | Low | Low | No | 2026-02-18 00:00-02:00 | None | [Link] | [Link] | Ready for Deploy | 2026-02-05 | 2026-02-18 |  | [Link] | [Link]
UPG-004 | ElastiCache Redis 7.0 Upgrade | ElastiCache | 6.2 | 7.0 | QA | us-west-2 | Emily Davis | Platform | P2 - High | Medium | Medium | Yes | 2026-02-22 04:00-06:00 | Session handling update | [Link] | [Link] | In Progress | 2026-02-08 | 2026-02-22 |  | [Link] | [Link]
UPG-005 | API Gateway v2 Migration | API Gateway | REST API | HTTP API | PROD | us-east-1 | Alex Brown | API | P1 - Critical | Critical | High | No | 2026-03-01 02:00-04:00 | Lambda integration update, Route changes | [Link] | [Link] | Not Started | 2026-02-15 | 2026-03-01 |  | [Link] | [Link]
UPG-006 | Aurora MySQL 8.0 Upgrade | Aurora | 5.7 | 8.0 | UAT | us-east-1 | Sarah Johnson | Database | P1 - Critical | High | High | Yes | 2026-02-25 01:00-05:00 | Query compatibility, Index optimization | [Link] | [Link] | Blocked | 2026-02-12 | 2026-02-25 |  | [Link] | [Link]
UPG-007 | Lambda Runtime Node.js 20 | Lambda | 18.x | 20.x | QA | us-east-1 | Chris Wilson | Serverless | P3 - Medium | Low | Low | No | N/A | None | [Link] | [Link] | Validated | 2026-01-20 | 2026-02-01 |  | [Link] | [Link]
UPG-008 | CloudFront TLS 1.3 Enable | CloudFront | TLS 1.2 | TLS 1.3 | PROD | Global | Mike Chen | Network | P2 - High | Low | None | No | N/A | Client compatibility verification | [Link] | [Link] | Deployed | 2026-01-25 | 2026-02-05 |  | [Link] | [Link]

## Environment Plan
Environment Rollout Plan - QA / UAT / PROD
QA ENVIRONMENT
ID | Component | Rollout Window | Change Freeze | Dependencies | Cutover Steps | Rollback Trigger | Status
UPG-001 | EKS 1.29 | 2026-02-15 02:00-06:00 | Feb 10-12 | Node group ready | 1. Drain nodes 2. Upgrade control plane 3. Upgrade nodes | Pod failures > 5% | In Progress
UPG-002 | RDS PostgreSQL 16 | 2026-02-20 03:00-07:00 | Feb 18-19 | Backup verified | 1. Create snapshot 2. Upgrade 3. Validate | Connection errors | Not Started
UPG-004 | ElastiCache 7.0 | 2026-02-22 04:00-06:00 | Feb 21 | Session migration | 1. Create new cluster 2. Sync data 3. Switch endpoint | Cache miss > 20% | In Progress
UPG-007 | Lambda Node 20 | N/A (Rolling) | None | None | 1. Update runtime 2. Deploy 3. Test | Error rate > 1% | Validated
UAT ENVIRONMENT
ID | Component | Rollout Window | Change Freeze | Dependencies | Cutover Steps | Rollback Trigger | Status
UPG-003 | ALB Firmware | 2026-02-18 00:00-02:00 | None | None | 1. Apply update 2. Verify health checks | 5xx errors > 1% | Ready for Deploy
UPG-006 | Aurora MySQL 8.0 | 2026-02-25 01:00-05:00 | Feb 23-24 | QA validation complete | 1. Create clone 2. Upgrade clone 3. Test 4. Cutover | Query failures | Blocked
PROD ENVIRONMENT
ID | Component | Rollout Window | Change Freeze | Dependencies | Cutover Steps | Rollback Trigger | Status
UPG-005 | API Gateway v2 | 2026-03-01 02:00-04:00 | Feb 28 - Mar 1 | UAT sign-off, CAB approval | 1. Deploy canary 2. Shift 10% traffic 3. Monitor 4. Full cutover | Latency > 500ms Error rate > 0.5% | Not Started
UPG-008 | CloudFront TLS 1.3 | N/A (Non-disruptive) | None | Client compatibility verified | 1. Update security policy 2. Monitor | SSL errors | Deployed
CHANGE FREEZE CALENDAR
Period | Environment | Reason | Exceptions
Feb 14-16, 2026 | ALL | Valentine's Day Traffic Peak | Critical security patches only
Mar 15-20, 2026 | PROD | End of Quarter Processing | None
Apr 1-5, 2026 | ALL | Fiscal Year End | Emergency fixes only with VP approval

## Testing & Validation
Testing & Validation Tracker
Upgrade ID | Test Case ID | Test Category | Test Description | Environment | Tester | Test Date | Result | Evidence Link | Rollback Verified | Rollback Evidence | Notes
UPG-001 | TC-001-01 | Functional | Verify pod scheduling after upgrade | QA | QA Team | 2026-02-10 | Pass | [Link] | Yes | [Link]
UPG-001 | TC-001-02 | Functional | Verify HPA scaling behavior | QA | QA Team | 2026-02-10 | Pass | [Link] | Yes | [Link]
UPG-001 | TC-001-03 | Performance | Load test - 1000 RPS | QA | Perf Team | 2026-02-11 | Pass | [Link] | N/A |  | P99 latency: 45ms
UPG-001 | TC-001-04 | Integration | Verify service mesh connectivity | QA | QA Team | 2026-02-11 | Pass | [Link] | Yes | [Link]
UPG-002 | TC-002-01 | Functional | Verify read replicas sync | QA | DBA |  | Pending |  | No |  | Scheduled for Feb 15
UPG-002 | TC-002-02 | Functional | Verify application queries | QA | Dev Team |  | Pending |  | No
UPG-004 | TC-004-01 | Functional | Verify session persistence | QA | QA Team | 2026-02-12 | Pass | [Link] | Yes | [Link]
UPG-004 | TC-004-02 | Performance | Cache hit ratio > 95% | QA | Perf Team | 2026-02-12 | Pass | [Link] | N/A |  | Hit ratio: 97.2%
UPG-006 | TC-006-01 | Functional | Query compatibility test | UAT | DBA | 2026-02-14 | Fail | [Link] | Yes | [Link] | 3 queries need rewrite
UPG-007 | TC-007-01 | Functional | Lambda cold start test | QA | QA Team | 2026-01-28 | Pass | [Link] | Yes | [Link]
UPG-007 | TC-007-02 | Functional | Lambda memory usage | QA | QA Team | 2026-01-28 | Pass | [Link] | N/A |  | Memory: 128MB avg
UPG-008 | TC-008-01 | Security | TLS handshake verification | PROD | Security | 2026-02-03 | Pass | [Link] | N/A

## Risks & Issues
Risk Register & Issue Tracker
RISK REGISTER
Risk ID | Related Upgrade | Risk Description | Category | Probability | Impact | Risk Score | Mitigation Plan | Contingency | Owner | Status | Escalation Path
R-001 | UPG-001 | EKS upgrade may cause pod disruption | Technical | Medium | High | High | Use PodDisruptionBudgets, rolling upgrade | Rollback to 1.27 | John Smith | Mitigated | Platform Lead → VP Eng
R-002 | UPG-002 | PostgreSQL 16 query incompatibility | Technical | High | High | Critical | Full regression test, query analysis | Delay upgrade, rewrite queries | Sarah Johnson | Open | DBA Lead → CTO
R-003 | UPG-005 | API Gateway migration affects clients | Business | Medium | High | High | Canary deployment, client notification | Maintain both APIs | Alex Brown | Open | API Team → Product
R-004 | UPG-006 | Aurora upgrade exceeds maintenance window | Schedule | High | Medium | High | Pre-upgrade optimization, parallel clone | Extend window with approval | Sarah Johnson | Open | DBA → VP Eng
R-005 | UPG-004 | Redis cluster failover during upgrade | Technical | Low | Medium | Medium | Use Global Datastore, test failover | Switch to backup cluster | Emily Davis | Mitigated | Platform → SRE
ACTIVE ISSUES
Issue ID | Related Upgrade | Issue Description | Severity | Reported By | Reported Date | Assigned To | Resolution | Target Date | Status
I-001 | UPG-006 | 3 legacy queries fail on MySQL 8.0 syntax | High | DBA Team | 2026-02-14 | Dev Team | Rewrite queries to use new syntax | 2026-02-18 | In Progress
I-002 | UPG-001 | Prometheus metrics missing after node upgrade | Medium | SRE Team | 2026-02-12 | Platform Team | Update Prometheus scrape config | 2026-02-13 | Resolved
I-003 | UPG-005 | Legacy client using deprecated API feature | High | API Team | 2026-02-15 | Client Success | Client migration support needed | 2026-02-25 | Open

## Approvals & Change Log
Approvals & Change Log
CAB APPROVALS
Upgrade ID | Component | Environment | CAB Meeting Date | Presenter | Approval Status | Approved By | Conditions | Approval Date | Notes
UPG-001 | EKS 1.29 | QA | 2026-02-05 | John Smith | Approved | CAB Chair | None | 2026-02-05 | Proceed with QA
UPG-002 | RDS PostgreSQL | QA | 2026-02-05 | Sarah Johnson | Approved | CAB Chair | Full backup required | 2026-02-05
UPG-003 | ALB | UAT | 2026-02-12 | Mike Chen | Approved | CAB Chair | Off-peak hours only | 2026-02-12
UPG-005 | API Gateway | PROD | Pending | Alex Brown | Pending |  |  |  | Scheduled for Feb 26 CAB
UPG-006 | Aurora MySQL | UAT | 2026-02-12 | Sarah Johnson | Conditional | CAB Chair | Query fixes required first | 2026-02-12 | Blocked until I-001 resolved
UPG-008 | CloudFront TLS | PROD | 2026-01-29 | Mike Chen | Approved | CAB Chair | None | 2026-01-29 | Low risk, approved
ENVIRONMENT SIGN-OFFS
Upgrade ID | Environment | Technical Lead | Tech Sign-off Date | QA Lead | QA Sign-off Date | Business Owner | Business Sign-off Date | Final Status
UPG-007 | QA | Chris Wilson | 2026-01-28 | QA Lead | 2026-01-29 | Product Owner | 2026-01-29 | Complete
UPG-008 | PROD | Mike Chen | 2026-02-03 | QA Lead | 2026-02-03 | Product Owner | 2026-02-04 | Complete
UPG-001 | QA | John Smith | Pending |  |  |  |  | In Progress
CHANGE LOG
Timestamp | Upgrade ID | Action | Changed By | Previous Value | New Value | Reason
2026-02-14 16:30 | UPG-006 | Status Change | Sarah Johnson | In Progress | Blocked | Query compatibility issues found
2026-02-14 10:15 | UPG-003 | Status Change | Mike Chen | In Progress | Ready for Deploy | All tests passed
2026-02-13 14:00 | UPG-001 | Target Date Change | John Smith | 2026-02-12 | 2026-02-15 | Extended for additional testing
2026-02-12 09:30 | UPG-004 | Risk Level Change | Emily Davis | High | Medium | Mitigation plan implemented
2026-02-10 11:00 | UPG-002 | Owner Change | Admin | TBD | Sarah Johnson | Assignment completed
2026-02-05 15:45 | UPG-008 | Status Change | Mike Chen | Ready for Deploy | Deployed | Deployment successful
2026-02-03 10:00 | UPG-008 | Status Change | Mike Chen | Deployed | Validated | Post-deployment validation complete
RELEASE NOTES
Upgrade ID | Version | Release Date | Summary | Breaking Changes | Migration Steps | Documentation Link
UPG-007 | Node.js 20.x | 2026-02-01 | Lambda runtime upgrade to Node.js 20 | None | Update runtime in function config | [Confluence Link]
UPG-008 | TLS 1.3 | 2026-02-05 | Enabled TLS 1.3 on CloudFront distributions | Clients must support TLS 1.2+ | None required | [Confluence Link]